## Slide 1: Robot Project Meeting – 22/11/2018
Bourgogne, Colrat, Evaux, Gaizi, Nicolle – ACE TEAM

## Slide 2: Last Meeting:
These were the points discussed:
  Use a GUI (maybe the one from the Safety Kit, or make one of our own) to communicate with the robot and get information from the robot instead of using the screen
  Think about making the two first modes of the robot around the middle of January to have a clear vision of what could be shown at Embedded World
  Add a rubber band to the robot’s wheels to reduce slipping
To be done:
  @All students: Divide your tasks into brief and concise tasks, make a calendar of small achievable deadlines and stick to it.
  @Virgile: Call IT every day until they fix your issue with Github
  @Amine: Add rubber band and test the slipping

## Slide 3: Points to discuss
No update regarding the material order ?
Precise the bill of specification for the robot`s functionning modes
  1st mode: remote control using bluetooth
  2nd mode: the robot runs away when there are obstacles
      We only implemented one Ultrasonic sensor that is looking forward, should we add more ?
      Beeping when the sensor detects something close ?
      Any other specification ?
  3rd mode: find numbers and avoid obstacles

## Slide 4: Subtasks: Amine Wheel enslavment
Done:
  Reshaped and optimized the movement control and enslvament code using interrupts only so it can be used with Bluetooth module for the robot‘s 1st mode
Issues:
  One of the input pins of the encoder seems to not be working (even though it was before) – Solved
  Compiler license problem with BIFACES, I cannot build a project, which makes it impossible to continue - Solved
To Do:
    Test and correct the new Movements and P. Enslavement for all 4 directions Deadline: November 27th
  Make Bluetooth and Movements work together to achieve Mode 1 of the robot (with Virgile) Deadline: December 6th
  Work on Robot‘s Mode 2 with Marlon using Servomotors, Obstacle detection and Movement control (with Marlon)
          Deadline: Not yet defined

## Slide 5: Subtasks: Guillaume, gyroscope
Done:
  I2C works
Issue:
To do:
  Finish the data recovery and processing
    Deadline: Begining of next week
  Integrate the code into Amine movement program
    Deadline: Beginig of December
  Wiki
    Deadline: Middle of December
  Look at the possible noise which appears when the mpu92/65 gets the info
  Deadline: Begining of January

## Slide 6: Subtasks: Virgile, Bluetooth communication
Done:
  Implement and test the Bluetooth capabilities in the final code
  Finish writing the wiki page
To Do:
  Create simplified GUI for PC to provide control and feedback to and from the robot.
          Deadline: December 5th

## Slide 7: Subtasks: Marlon - Servomotors
Done:
  Write the wiki page
  Change move servo function to take degree in parameter

## Slide 8: Substaks: Maxime, Camera
Done
  All the tasks are in progress
To Do
  Send video from the Aurix to the Raspberry by ethernet
    In progress
     End of November
  Take photos to pre-train our own CNN
    In progress : Tensorflow is now installed on Linux
    December 7th
  Bluetooth communication (Rasberry <-> Aurix Master)
    Aurix part : Done
    Rasberry part : In progress
    December 7th
  Documentation on Wiki page
    In progress
     When all the tasks will be done
Deadline : 19/12/18